## READ_ME
SYNTHETIC SAMPLE DATA — vendor accountability leaderboard
This workbook mirrors the STRUCTURE of a live data-centre commissioning tracker,
but every value here is INVENTED. No real vendors, people, sites or figures appear.
Safe to hand to Claude Code for building and experimentation.
Sheets:
Observations - obs records, one row each, with a responsible Company
Punch_List - punch items, one row each, with a responsible Company
Actions - actions/decisions, one row each, with a responsible Company
QAQC_Items - QA/QC + Cx items, one row each, with a responsible Company
Vendor_Scorecard - the TARGET leaderboard, aggregated from the four sheets above
Lookups - valid values (statuses, priority, RAG, systems, vendor list)
The leaderboard answers: 'who is holding the programme back?' — ranked by Total Overdue.
Vendor_Scorecard is built with live COUNTIF/COUNTIFS formulas so you can see the logic.

## Observations
Obs ID | Company | System | Title / Description | Status | Priority | Date Raised | Due Date | Days Overdue
OBS-001 | Apex M&E | Mechanical | Mechanical item OBS-001 — sample text | In Progress | Critical | 2026-03-01 | 2026-06-30 | 0
OBS-002 | Northwind Power | Electrical | Electrical item OBS-002 — sample text | In Progress | High | 2026-03-01 | 2026-06-30 | 0
OBS-003 | Northwind Power | Hydraulic | Electrical item OBS-003 — sample text | Open | Low | 2026-03-01 | 2026-06-30 | 0
OBS-004 | Northwind Power | Civil | Electrical item OBS-004 — sample text | In Progress | High | 2026-03-01 | 2026-06-30 | 0
OBS-005 | Northwind Power | Fire | Electrical item OBS-005 — sample text | Void | High | 2026-03-01 | 2026-06-30 | 0
OBS-006 | Northwind Power | Security | Electrical item OBS-006 — sample text | In Progress | Critical | 2026-03-01 | 2026-06-30 | 0
OBS-007 | Northwind Power | Civil | Electrical item OBS-007 — sample text | In Progress | Critical | 2026-03-01 | 2026-06-30 | 0
OBS-008 | Northwind Power | Security | Electrical item OBS-008 — sample text | Closed | Critical | 2026-03-01 | 2026-06-30 | 0
OBS-009 | Northwind Power | BMS | Electrical item OBS-009 — sample text | Void | High | 2026-03-01 | 2026-06-30 | 0
OBS-010 | Vanguard Controls | Electrical | BMS item OBS-010 — sample text | Open | High | 2026-03-01 | 2026-06-30 | 0
OBS-011 | Meridian Cooling | Mechanical | Mechanical item OBS-011 — sample text | In Progress | Medium | 2026-03-01 | 2026-06-30 | 0
OBS-012 | Orbit Switchgear | BMS | Electrical item OBS-012 — sample text | In Progress | High | 2026-03-01 | 2026-06-30 | 0
OBS-013 | Orbit Switchgear | Security | Electrical item OBS-013 — sample text | Open | Medium | 2026-03-01 | 2026-06-30 | 11
OBS-014 | Orbit Switchgear | Hydraulic | Electrical item OBS-014 — sample text | Closed | Medium | 2026-03-01 | 2026-06-30 | 0
OBS-015 | Orbit Switchgear | Mechanical | Electrical item OBS-015 — sample text | Closed | Critical | 2026-03-01 | 2026-06-30 | 0
OBS-016 | Orbit Switchgear | Fire | Electrical item OBS-016 — sample text | Void | Critical | 2026-03-01 | 2026-06-30 | 0
OBS-017 | Falcon Fire | Mechanical | Fire item OBS-017 — sample text | Void | Low | 2026-03-01 | 2026-06-30 | 0
OBS-018 | Falcon Fire | Mechanical | Fire item OBS-018 — sample text | In Progress | High | 2026-03-01 | 2026-06-30 | 0
OBS-019 | Falcon Fire | Hydraulic | Fire item OBS-019 — sample text | Void | Low | 2026-03-01 | 2026-06-30 | 0
OBS-020 | Helios Energy | Electrical | Electrical item OBS-020 — sample text | Open | Critical | 2026-03-01 | 2026-06-30 | 33
OBS-021 | Helios Energy | Hydraulic | Electrical item OBS-021 — sample text | Closed | High | 2026-03-01 | 2026-06-30 | 0
OBS-022 | Helios Energy | BMS | Electrical item OBS-022 — sample text | Void | Critical | 2026-03-01 | 2026-06-30 | 0
OBS-023 | Helios Energy | BMS | Electrical item OBS-023 — sample text | In Progress | Critical | 2026-03-01 | 2026-06-30 | 0
OBS-024 | Helios Energy | Hydraulic | Electrical item OBS-024 — sample text | Closed | Medium | 2026-03-01 | 2026-06-30 | 0
OBS-025 | Helios Energy | Electrical | Electrical item OBS-025 — sample text | Void | Medium | 2026-03-01 | 2026-06-30 | 0
OBS-026 | Granite Civils | BMS | Civil item OBS-026 — sample text | Open | High | 2026-03-01 | 2026-06-30 | 0
OBS-027 | Granite Civils | Civil | Civil item OBS-027 — sample text | Open | High | 2026-03-01 | 2026-06-30 | 0
OBS-028 | Granite Civils | BMS | Civil item OBS-028 — sample text | Open | Medium | 2026-03-01 | 2026-06-30 | 0
OBS-029 | Granite Civils | Civil | Civil item OBS-029 — sample text | Open | Medium | 2026-03-01 | 2026-06-30 | 0
OBS-030 | Granite Civils | Electrical | Civil item OBS-030 — sample text | Open | Low | 2026-03-01 | 2026-06-30 | 0
OBS-031 | Granite Civils | Mechanical | Civil item OBS-031 — sample text | Closed | Low | 2026-03-01 | 2026-06-30 | 0
OBS-032 | Beacon BMS | Hydraulic | BMS item OBS-032 — sample text | In Progress | Medium | 2026-03-01 | 2026-06-30 | 0
OBS-033 | Beacon BMS | Electrical | BMS item OBS-033 — sample text | In Progress | High | 2026-03-01 | 2026-06-30 | 29
OBS-034 | Beacon BMS | BMS | BMS item OBS-034 — sample text | In Progress | High | 2026-03-01 | 2026-06-30 | 0
OBS-035 | Beacon BMS | Electrical | BMS item OBS-035 — sample text | Open | Medium | 2026-03-01 | 2026-06-30 | 0
OBS-036 | Beacon BMS | Mechanical | BMS item OBS-036 — sample text | Open | High | 2026-03-01 | 2026-06-30 | 18
OBS-037 | Beacon BMS | Mechanical | BMS item OBS-037 — sample text | Void | Low | 2026-03-01 | 2026-06-30 | 0
OBS-038 | Beacon BMS | Electrical | BMS item OBS-038 — sample text | Closed | Critical | 2026-03-01 | 2026-06-30 | 0
OBS-039 | Beacon BMS | Security | BMS item OBS-039 — sample text | Void | Low | 2026-03-01 | 2026-06-30 | 0
OBS-040 | Summit Security | Hydraulic | Security item OBS-040 — sample text | Closed | Critical | 2026-03-01 | 2026-06-30 | 0
OBS-041 | Summit Security | Mechanical | Security item OBS-041 — sample text | In Progress | High | 2026-03-01 | 2026-06-30 | 0
OBS-042 | Summit Security | Mechanical | Security item OBS-042 — sample text | In Progress | Medium | 2026-03-01 | 2026-06-30 | 9
OBS-043 | Summit Security | Electrical | Security item OBS-043 — sample text | Open | Critical | 2026-03-01 | 2026-06-30 | 0
OBS-044 | Summit Security | Mechanical | Security item OBS-044 — sample text | Closed | Low | 2026-03-01 | 2026-06-30 | 0
OBS-045 | Summit Security | Electrical | Security item OBS-045 — sample text | Open | High | 2026-03-01 | 2026-06-30 | 56
OBS-046 | Summit Security | Fire | Security item OBS-046 — sample text | In Progress | Low | 2026-03-01 | 2026-06-30 | 17

## Punch_List
Punch ID | Company | System | Title / Description | Status | Priority | Date Raised | Due Date | Days Overdue
PL-001 | Apex M&E | Mechanical | Mechanical item PL-001 — sample text | Void | High | 2026-03-01 | 2026-06-30 | 0
PL-002 | Apex M&E | Hydraulic | Mechanical item PL-002 — sample text | Open | Medium | 2026-03-01 | 2026-06-30 | 0
PL-003 | Apex M&E | Electrical | Mechanical item PL-003 — sample text | Ready for Inspection | Critical | 2026-03-01 | 2026-06-30 | 0
PL-004 | Apex M&E | BMS | Mechanical item PL-004 — sample text | Closed | Critical | 2026-03-01 | 2026-06-30 | 0
PL-005 | Apex M&E | Security | Mechanical item PL-005 — sample text | Closed | Critical | 2026-03-01 | 2026-06-30 | 0
PL-006 | Apex M&E | BMS | Mechanical item PL-006 — sample text | Closed | Critical | 2026-03-01 | 2026-06-30 | 0
PL-007 | Apex M&E | Hydraulic | Mechanical item PL-007 — sample text | Void | Medium | 2026-03-01 | 2026-06-30 | 0
PL-008 | Apex M&E | Hydraulic | Mechanical item PL-008 — sample text | Closed | Medium | 2026-03-01 | 2026-06-30 | 0
PL-009 | Northwind Power | Security | Electrical item PL-009 — sample text | Open | Medium | 2026-03-01 | 2026-06-30 | 0
PL-010 | Northwind Power | Electrical | Electrical item PL-010 — sample text | Closed | Low | 2026-03-01 | 2026-06-30 | 0
PL-011 | Northwind Power | Electrical | Electrical item PL-011 — sample text | Closed | High | 2026-03-01 | 2026-06-30 | 0
PL-012 | Vanguard Controls | Mechanical | BMS item PL-012 — sample text | In Progress | Medium | 2026-03-01 | 2026-06-30 | 0
PL-013 | Vanguard Controls | BMS | BMS item PL-013 — sample text | In Progress | Critical | 2026-03-01 | 2026-06-30 | 0
PL-014 | Vanguard Controls | Hydraulic | BMS item PL-014 — sample text | Void | Critical | 2026-03-01 | 2026-06-30 | 0
PL-015 | Vanguard Controls | Fire | BMS item PL-015 — sample text | Closed | Critical | 2026-03-01 | 2026-06-30 | 0
PL-016 | Vanguard Controls | Fire | BMS item PL-016 — sample text | Closed | Medium | 2026-03-01 | 2026-06-30 | 0
PL-017 | Vanguard Controls | Mechanical | BMS item PL-017 — sample text | Void | Medium | 2026-03-01 | 2026-06-30 | 0
PL-018 | Vanguard Controls | Electrical | BMS item PL-018 — sample text | In Progress | Low | 2026-03-01 | 2026-06-30 | 0
PL-019 | Vanguard Controls | Electrical | BMS item PL-019 — sample text | Closed | Medium | 2026-03-01 | 2026-06-30 | 0
PL-020 | Meridian Cooling | Mechanical | Mechanical item PL-020 — sample text | Void | Low | 2026-03-01 | 2026-06-30 | 0
PL-021 | Meridian Cooling | BMS | Mechanical item PL-021 — sample text | Void | Critical | 2026-03-01 | 2026-06-30 | 0
PL-022 | Orbit Switchgear | BMS | Electrical item PL-022 — sample text | Ready for Inspection | Critical | 2026-03-01 | 2026-06-30 | 0
PL-023 | Falcon Fire | Security | Fire item PL-023 — sample text | Closed | High | 2026-03-01 | 2026-06-30 | 0
PL-024 | Falcon Fire | Fire | Fire item PL-024 — sample text | In Progress | High | 2026-03-01 | 2026-06-30 | 0
PL-025 | Falcon Fire | Fire | Fire item PL-025 — sample text | Closed | Low | 2026-03-01 | 2026-06-30 | 0
PL-026 | Falcon Fire | Mechanical | Fire item PL-026 — sample text | Closed | High | 2026-03-01 | 2026-06-30 | 0
PL-027 | Falcon Fire | Security | Fire item PL-027 — sample text | Closed | Critical | 2026-03-01 | 2026-06-30 | 0
PL-028 | Helios Energy | Civil | Electrical item PL-028 — sample text | Void | Low | 2026-03-01 | 2026-06-30 | 0
PL-029 | Helios Energy | Fire | Electrical item PL-029 — sample text | Closed | High | 2026-03-01 | 2026-06-30 | 0
PL-030 | Granite Civils | Mechanical | Civil item PL-030 — sample text | Open | High | 2026-03-01 | 2026-06-30 | 55
PL-031 | Beacon BMS | Hydraulic | BMS item PL-031 — sample text | Open | High | 2026-03-01 | 2026-06-30 | 0
PL-032 | Beacon BMS | Civil | BMS item PL-032 — sample text | In Progress | Medium | 2026-03-01 | 2026-06-30 | 0
PL-033 | Beacon BMS | Electrical | BMS item PL-033 — sample text | Ready for Inspection | Critical | 2026-03-01 | 2026-06-30 | 0
PL-034 | Beacon BMS | Mechanical | BMS item PL-034 — sample text | Void | Medium | 2026-03-01 | 2026-06-30 | 0
PL-035 | Beacon BMS | Hydraulic | BMS item PL-035 — sample text | Ready for Inspection | Medium | 2026-03-01 | 2026-06-30 | 0
PL-036 | Beacon BMS | BMS | BMS item PL-036 — sample text | Ready for Inspection | High | 2026-03-01 | 2026-06-30 | 8
PL-037 | Beacon BMS | BMS | BMS item PL-037 — sample text | Ready for Inspection | High | 2026-03-01 | 2026-06-30 | 0
PL-038 | Summit Security | BMS | Security item PL-038 — sample text | Ready for Inspection | Medium | 2026-03-01 | 2026-06-30 | 0
PL-039 | Summit Security | Hydraulic | Security item PL-039 — sample text | Closed | Medium | 2026-03-01 | 2026-06-30 | 0
PL-040 | Summit Security | Security | Security item PL-040 — sample text | Ready for Inspection | Medium | 2026-03-01 | 2026-06-30 | 0
PL-041 | Summit Security | Security | Security item PL-041 — sample text | Closed | Low | 2026-03-01 | 2026-06-30 | 0
PL-042 | Summit Security | BMS | Security item PL-042 — sample text | Closed | Medium | 2026-03-01 | 2026-06-30 | 0

## Actions
Action ID | Company | Type | Description | Status | Priority | Date Raised | Due Date | Days Overdue
ACT-001 | Apex M&E | Action | Action item ACT-001 — sample text | Open | Low | 2026-03-01 | 2026-06-30 | 0
ACT-002 | Apex M&E | Decision | Decision item ACT-002 — sample text | Cancelled | Low | 2026-03-01 | 2026-06-30 | 0
ACT-003 | Apex M&E | Risk | Risk item ACT-003 — sample text | Open | High | 2026-03-01 | 2026-06-30 | 33
ACT-004 | Apex M&E | Risk | Risk item ACT-004 — sample text | Cancelled | Medium | 2026-03-01 | 2026-06-30 | 0
ACT-005 | Apex M&E | Action | Action item ACT-005 — sample text | Open | High | 2026-03-01 | 2026-06-30 | 0
ACT-006 | Apex M&E | Risk | Risk item ACT-006 — sample text | Open | Critical | 2026-03-01 | 2026-06-30 | 16
ACT-007 | Northwind Power | Decision | Decision item ACT-007 — sample text | Open | Low | 2026-03-01 | 2026-06-30 | 46
ACT-008 | Northwind Power | Decision | Decision item ACT-008 — sample text | Open | High | 2026-03-01 | 2026-06-30 | 0
ACT-009 | Northwind Power | Action | Action item ACT-009 — sample text | In Progress | Low | 2026-03-01 | 2026-06-30 | 0
ACT-010 | Northwind Power | Decision | Decision item ACT-010 — sample text | In Progress | Low | 2026-03-01 | 2026-06-30 | 0
ACT-011 | Northwind Power | Action | Action item ACT-011 — sample text | Cancelled | Low | 2026-03-01 | 2026-06-30 | 0
ACT-012 | Northwind Power | Risk | Risk item ACT-012 — sample text | Open | Low | 2026-03-01 | 2026-06-30 | 0
ACT-013 | Northwind Power | Decision | Decision item ACT-013 — sample text | Cancelled | Critical | 2026-03-01 | 2026-06-30 | 0
ACT-014 | Vanguard Controls | Action | Action item ACT-014 — sample text | In Progress | High | 2026-03-01 | 2026-06-30 | 0
ACT-015 | Vanguard Controls | Action | Action item ACT-015 — sample text | Open | Low | 2026-03-01 | 2026-06-30 | 0
ACT-016 | Vanguard Controls | Action | Action item ACT-016 — sample text | In Progress | Low | 2026-03-01 | 2026-06-30 | 0
ACT-017 | Vanguard Controls | Decision | Decision item ACT-017 — sample text | Open | Critical | 2026-03-01 | 2026-06-30 | 55
ACT-018 | Meridian Cooling | Risk | Risk item ACT-018 — sample text | In Progress | High | 2026-03-01 | 2026-06-30 | 55
ACT-019 | Meridian Cooling | Action | Action item ACT-019 — sample text | In Progress | Low | 2026-03-01 | 2026-06-30 | 28
ACT-020 | Meridian Cooling | Decision | Decision item ACT-020 — sample text | In Progress | High | 2026-03-01 | 2026-06-30 | 0
ACT-021 | Meridian Cooling | Decision | Decision item ACT-021 — sample text | Complete | Critical | 2026-03-01 | 2026-06-30 | 0
ACT-022 | Meridian Cooling | Action | Action item ACT-022 — sample text | In Progress | Critical | 2026-03-01 | 2026-06-30 | 9
ACT-023 | Orbit Switchgear | Decision | Decision item ACT-023 — sample text | Open | Low | 2026-03-01 | 2026-06-30 | 0
ACT-024 | Orbit Switchgear | Decision | Decision item ACT-024 — sample text | In Progress | Critical | 2026-03-01 | 2026-06-30 | 0
ACT-025 | Orbit Switchgear | Decision | Decision item ACT-025 — sample text | Complete | High | 2026-03-01 | 2026-06-30 | 0
ACT-026 | Orbit Switchgear | Action | Action item ACT-026 — sample text | Complete | High | 2026-03-01 | 2026-06-30 | 0
ACT-027 | Falcon Fire | Action | Action item ACT-027 — sample text | Complete | High | 2026-03-01 | 2026-06-30 | 0
ACT-028 | Falcon Fire | Decision | Decision item ACT-028 — sample text | Open | Medium | 2026-03-01 | 2026-06-30 | 0
ACT-029 | Falcon Fire | Risk | Risk item ACT-029 — sample text | Complete | Critical | 2026-03-01 | 2026-06-30 | 0
ACT-030 | Helios Energy | Risk | Risk item ACT-030 — sample text | Complete | Critical | 2026-03-01 | 2026-06-30 | 0
ACT-031 | Helios Energy | Decision | Decision item ACT-031 — sample text | Cancelled | High | 2026-03-01 | 2026-06-30 | 0
ACT-032 | Granite Civils | Action | Action item ACT-032 — sample text | Complete | Medium | 2026-03-01 | 2026-06-30 | 0
ACT-033 | Beacon BMS | Decision | Decision item ACT-033 — sample text | Complete | Low | 2026-03-01 | 2026-06-30 | 0
ACT-034 | Summit Security | Decision | Decision item ACT-034 — sample text | In Progress | Critical | 2026-03-01 | 2026-06-30 | 1
ACT-035 | Summit Security | Risk | Risk item ACT-035 — sample text | In Progress | High | 2026-03-01 | 2026-06-30 | 41
ACT-036 | Summit Security | Decision | Decision item ACT-036 — sample text | In Progress | Low | 2026-03-01 | 2026-06-30 | 40
ACT-037 | Summit Security | Decision | Decision item ACT-037 — sample text | Cancelled | High | 2026-03-01 | 2026-06-30 | 0
ACT-038 | Summit Security | Decision | Decision item ACT-038 — sample text | Complete | Low | 2026-03-01 | 2026-06-30 | 0

## QAQC_Items
Item ID | Company | System | Stage | Status | Date Raised | Due Date | Days Overdue
QC-001 | Apex M&E | Fire | FATs | Closed | 2026-03-01 | 2026-06-30 | 0
QC-002 | Apex M&E | Mechanical | Tech Sub | In Progress | 2026-03-01 | 2026-06-30 | 12
QC-003 | Apex M&E | Fire | CxA Sign Off | Closed | 2026-03-01 | 2026-06-30 | 0
QC-004 | Northwind Power | Hydraulic | Pre-Energisation | Open | 2026-03-01 | 2026-06-30 | 0
QC-005 | Northwind Power | Hydraulic | CxA Sign Off | Open | 2026-03-01 | 2026-06-30 | 45
QC-006 | Northwind Power | Mechanical | Closeout | Open | 2026-03-01 | 2026-06-30 | 0
QC-007 | Northwind Power | Hydraulic | Pre-Energisation | Closed | 2026-03-01 | 2026-06-30 | 0
QC-008 | Northwind Power | Fire | Pre-Energisation | In Progress | 2026-03-01 | 2026-06-30 | 0
QC-009 | Northwind Power | Hydraulic | CxA Sign Off | In Progress | 2026-03-01 | 2026-06-30 | 0
QC-010 | Northwind Power | Hydraulic | Closeout | Open | 2026-03-01 | 2026-06-30 | 0
QC-011 | Northwind Power | Fire | Closeout | In Progress | 2026-03-01 | 2026-06-30 | 0
QC-012 | Vanguard Controls | Fire | CxA Sign Off | Open | 2026-03-01 | 2026-06-30 | 0
QC-013 | Vanguard Controls | Hydraulic | As Built | Closed | 2026-03-01 | 2026-06-30 | 0
QC-014 | Vanguard Controls | Electrical | Pre-Energisation | Closed | 2026-03-01 | 2026-06-30 | 0
QC-015 | Vanguard Controls | Security | FATs | Closed | 2026-03-01 | 2026-06-30 | 0
QC-016 | Vanguard Controls | Electrical | As Built | Open | 2026-03-01 | 2026-06-30 | 17
QC-017 | Meridian Cooling | Civil | Power On Request | Open | 2026-03-01 | 2026-06-30 | 0
QC-018 | Meridian Cooling | BMS | Power On Request | Open | 2026-03-01 | 2026-06-30 | 8
QC-019 | Meridian Cooling | Security | Tech Sub | Closed | 2026-03-01 | 2026-06-30 | 0
QC-020 | Meridian Cooling | BMS | Closeout | In Progress | 2026-03-01 | 2026-06-30 | 0
QC-021 | Meridian Cooling | Hydraulic | FATs | Closed | 2026-03-01 | 2026-06-30 | 0
QC-022 | Meridian Cooling | Mechanical | Closeout | Open | 2026-03-01 | 2026-06-30 | 0
QC-023 | Orbit Switchgear | Fire | Closeout | In Progress | 2026-03-01 | 2026-06-30 | 45
QC-024 | Orbit Switchgear | Electrical | Pre-Energisation | In Progress | 2026-03-01 | 2026-06-30 | 45
QC-025 | Falcon Fire | Security | FATs | Closed | 2026-03-01 | 2026-06-30 | 0
QC-026 | Falcon Fire | Civil | Power On Request | Open | 2026-03-01 | 2026-06-30 | 0
QC-027 | Falcon Fire | BMS | Pre-Energisation | Open | 2026-03-01 | 2026-06-30 | 0
QC-028 | Falcon Fire | Hydraulic | FATs | In Progress | 2026-03-01 | 2026-06-30 | 0
QC-029 | Helios Energy | BMS | CxA Sign Off | In Progress | 2026-03-01 | 2026-06-30 | 0
QC-030 | Helios Energy | BMS | As Built | Closed | 2026-03-01 | 2026-06-30 | 0
QC-031 | Helios Energy | Civil | Pre-Energisation | Open | 2026-03-01 | 2026-06-30 | 0
QC-032 | Helios Energy | Security | Closeout | Closed | 2026-03-01 | 2026-06-30 | 0
QC-033 | Granite Civils | Electrical | CxA Sign Off | In Progress | 2026-03-01 | 2026-06-30 | 41
QC-034 | Granite Civils | Civil | As Built | In Progress | 2026-03-01 | 2026-06-30 | 0
QC-035 | Granite Civils | Civil | FATs | In Progress | 2026-03-01 | 2026-06-30 | 19
QC-036 | Granite Civils | Electrical | Pre-Energisation | In Progress | 2026-03-01 | 2026-06-30 | 0
QC-037 | Beacon BMS | Hydraulic | Closeout | Closed | 2026-03-01 | 2026-06-30 | 0
QC-038 | Beacon BMS | BMS | Tech Sub | Open | 2026-03-01 | 2026-06-30 | 0
QC-039 | Beacon BMS | Mechanical | Tech Sub | Closed | 2026-03-01 | 2026-06-30 | 0
QC-040 | Beacon BMS | Electrical | Power On Request | In Progress | 2026-03-01 | 2026-06-30 | 29
QC-041 | Beacon BMS | Hydraulic | CxA Sign Off | Closed | 2026-03-01 | 2026-06-30 | 0
QC-042 | Beacon BMS | Electrical | Pre-Energisation | Open | 2026-03-01 | 2026-06-30 | 36
QC-043 | Beacon BMS | Security | CxA Sign Off | Closed | 2026-03-01 | 2026-06-30 | 0
QC-044 | Beacon BMS | Security | FATs | Closed | 2026-03-01 | 2026-06-30 | 0
QC-045 | Summit Security | Civil | Closeout | Closed | 2026-03-01 | 2026-06-30 | 0
QC-046 | Summit Security | Security | Tech Sub | Closed | 2026-03-01 | 2026-06-30 | 0
QC-047 | Summit Security | Fire | Closeout | Open | 2026-03-01 | 2026-06-30 | 0
QC-048 | Summit Security | Fire | CxA Sign Off | In Progress | 2026-03-01 | 2026-06-30 | 0
QC-049 | Summit Security | Civil | Closeout | Closed | 2026-03-01 | 2026-06-30 | 0
QC-050 | Summit Security | BMS | Power On Request | In Progress | 2026-03-01 | 2026-06-30 | 0
QC-051 | Summit Security | Hydraulic | Pre-Energisation | In Progress | 2026-03-01 | 2026-06-30 | 0
QC-052 | Summit Security | Civil | Tech Sub | Closed | 2026-03-01 | 2026-06-30 | 0

## Vendor_Scorecard
Company | Open Obs | Open Punch | Open Actions | Overdue Obs | Overdue Punch | Overdue Actions | Overdue QAQC/Cx | Total Open | Total Overdue | RAG | Notes
Apex M&E | 1 | 2 | 4 | 0 | 0 | 2 | 1 | 7 | 3 | AMBER
Northwind Power | 5 | 1 | 5 | 0 | 0 | 1 | 1 | 11 | 2 | AMBER
Vanguard Controls | 1 | 3 | 4 | 0 | 0 | 1 | 1 | 8 | 2 | AMBER
Meridian Cooling | 1 | 0 | 4 | 0 | 0 | 3 | 1 | 5 | 4 | RED
Orbit Switchgear | 2 | 1 | 2 | 1 | 0 | 0 | 2 | 5 | 3 | AMBER
Falcon Fire | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | GREEN
Helios Energy | 2 | 0 | 0 | 1 | 0 | 0 | 0 | 2 | 1 | AMBER
Granite Civils | 5 | 1 | 0 | 0 | 1 | 0 | 2 | 6 | 3 | AMBER
Beacon BMS | 5 | 6 | 0 | 2 | 1 | 0 | 2 | 11 | 5 | RED
Summit Security | 5 | 2 | 3 | 3 | 0 | 3 | 0 | 10 | 6 | RED

## Lookups
Obs_Status | Punch_Status | Action_Status | Priority | RAG | System | Company
Open | Open | Open | Critical | GREEN | Electrical | Apex M&E
In Progress | In Progress | In Progress | High | AMBER | Mechanical | Northwind Power
Closed | Ready for Inspection | Complete | Medium | RED | Fire | Vanguard Controls
Void | Closed | Cancelled | Low |  | Security | Meridian Cooling
| Void |  |  |  | BMS | Orbit Switchgear
[5 empty] | Hydraulic | Falcon Fire
[5 empty] | Civil | Helios Energy
Granite Civils
Beacon BMS
Summit Security
RAG thresholds (Total Overdue):
GREEN = 0 ¦ AMBER = 1-3 ¦ RED = 4+ (tune to match your real thresholds)